## Export Summary
This document was exported from Numbers. Each table was converted to an Excel worksheet. All other objects on each Numbers sheet were placed on separate worksheets. Please be aware that formula calculations may differ in Excel.
Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
Product Backlog
| Table 1 | Product Backlog
Sprint 01 Backlog
| Table 1 | Sprint 01 Backlog
Sprint 02 Backlog
| Table 1 | Sprint 02 Backlog
Sprint 03 Backlog
| Table 1 | Sprint 03 Backlog
Sprint 04 Backlog
| Table 1 | Sprint 04 Backlog
Sprint 05 Backlog
| Table 1 | Sprint 05 Backlog

## Product Backlog
Product Name: | Exceptional Laptops and Supercomputers Always (ELSA) | [6 empty] | Complete Fields in Green!!!
Team ID: | 1001536613
| Team Member Name | [5 empty] | Initials | Student ID
Required | Devasri Warrier | [5 empty] | DW | 100
Sprint # | Remaining | Completed This Sprint |  |  |  | Comment
0 | 4 | 4 | 4 |  | Total | Kind of working, order
1 | 2 | 2 |  |  | 1 | Total features left at the end of Sprint #1
2 | 2 | 0 |  |  | 2 | Total features left at the end of Sprint #2
3 | 2 | 0 |  |  | 3 | ...and so on
4 | 2 | 0
5 | 2 | 0
Note: Priority and specs for unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
Additional features may be proposed by the student but must be approved by the Product Owner in writing
Sprints
Feature ID | Priority | Required | Bonus | Est | Planned | Status | As a... | I want to... | So that I can… | Notes
CUST | 1 | 1 |  | 3 | 1 | Finished in Sprint 1 | Sales Staff | Remember each customer’s name and contact info | Ship them products repeatedly
OPT | 2 | 1 |  | 8 |  | In Test | Inventory | Maintain a list of options for a desktop (e.g., disk, RAM, CPU) | Select them when designing a new desktop product
DESKT | 3 | 1 |  | 8 |  | In Work | Sales Staff | Define a new desktop configuration from options | Can quickly customize products for my customers
ORDER | 4 | 1 |  | 13 |  | Finished in Sprint 1 | Sales Staff | Associate a customer with one or more desktops into an order | Keep track of who has bought what

## Sprint 01 Backlog
Sprint # | 1 |  | Complete Fields in Green!!!
Start on | 2020-03-22 12:00 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2020-03-23
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 16
Day 1 Left | 13 | 3
Day 2 Left | 13 | 0
Day 3 Left | 13 | 0
Day 4 Left | 13 | 0
Day 5 Left | 13 | 0
Day 6 Left | 10 | 3
Day 7 Left | 1 | 9
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | CUST | DW | Write the Customer class | Completed Day 6 | Test each class and method as it is written
2 | CUST | DW | Write operator<< for Customer | Completed Day 6 | Commit and push AT LEAST once every class or update
3 | CUST | DW | Write Store::add_customer, num_customers, and customer | Completed Day 6
4 | OPT | DW | Write the Options class sans to_string | Completed Day 7
5 | OPT | DW | Write Options::to_string and its operator<< | Completed Day 7
6 | OPT | DW | Write Store::add_option (to Store), num_options, and option | Completed Day 7
7 | DESKT | DW | Write the Desktop class with add_option method | Completed Day 7 | Understand why it forever loops…
8 | DESKT | DW | Write the Desktop::price method | Completed Day 7
9 | DESKT | DW | Write operator<< for Desktop | Completed Day 7
10 | DESKT | DW | Write Store::new_desktop, add_option (to desktop), num_desktops, and desktop | Completed Day 7
11 | ORDER | DW | Write the Order associative class and constructor | Completed Day 7 | Understand why memory address prints..?
12 | ORDER | DW | Write Order::add_product | Completed Day 7
13 | ORDER | DW | Write Order::price | Completed Day 1
14 | ORDER | DW | Write Store::new_order, add_desktop, num_orders, and order | Completed Day 1
15 | ORDER | DW | Integrate and test with cse1325_prof/elsa/sprint_1/main.cpp | In Work
16 | ORDER | DW | Ensure ALL CODE is on GitHub by deadline! | Completed Day 1
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 02 Backlog
Sprint # | 2 |  | Complete Fields in Green!!!
Start on | 2020-03-23 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2020-03-30
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 1
Day 1 Left | 1 | 0
Day 2 Left | 1 | 0
Day 3 Left | 1 | 0
Day 4 Left | 1 | 0
Day 5 Left | 1 | 0
Day 6 Left | 1 | 0
Day 7 Left | 1 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 |  |  | --> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 03 Backlog
Sprint # | 3 |  | Complete Fields in Green!!!
Start on | 2020-03-30 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2020-04-06
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 1
Day 1 Left | 1 | 0
Day 2 Left | 1 | 0
Day 3 Left | 1 | 0
Day 4 Left | 1 | 0
Day 5 Left | 1 | 0
Day 6 Left | 1 | 0
Day 7 Left | 1 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 |  |  | --> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 04 Backlog
Sprint # | 4 |  | Complete Fields in Green!!!
Start on | 2020-04-06 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2020-04-20
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 1
Day 1 Left | 1 | 0
Day 2 Left | 1 | 0
Day 3 Left | 1 | 0
Day 4 Left | 1 | 0
Day 5 Left | 1 | 0
Day 6 Left | 1 | 0
Day 7 Left | 1 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 |  |  | --> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 05 Backlog
Sprint # | 5 |  | Complete Fields in Green!!!
Start on | 2020-04-20 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2020-04-27
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 1
Day 1 Left | 1 | 0
Day 2 Left | 1 | 0
Day 3 Left | 1 | 0
Day 4 Left | 1 | 0
Day 5 Left | 1 | 0
Day 6 Left | 1 | 0
Day 7 Left | 1 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 |  |  | --> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84