## Product Backlog
Product Name: | Exceptional Laptops and Supercomputers Always (ELSA) | [6 empty] | Complete Fields in Green!!!
Team ID: | Team Happy Face
| Team Member Name | [5 empty] | Initials | Student ID
Required | Devasri Warrier | [5 empty] | DW | 1001556613
Sprint # | Remaining | Completed This Sprint |  |  |  | Comment
0 | 22 |  |  |  | Total | Total number of features (in column H)
1 | 18 | 4 |  |  | 1 | Total features left at the end of Sprint #1
2 | 15 | 3 |  |  | 2 | Total features left at the end of Sprint #2
3 | 15 | 0 |  |  | 3 | ...and so on
4 | 10 | 5
5 | 5 | 5
Note: Priority and specs for unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
Additional features may be proposed by the student but must be approved by the Product Owner in writing
Sprints
Feature ID | Priority | Required | Bonus | Est | Planned | Status | As a... | I want to... | So that I can… | Notes
CUST | 1 | 1 |  | 3 | 1 | Finished in Sprint 1 | Sales Staff | Remember each customer’s name and contact info | Ship them products repeatedly
OPT | 2 | 1 |  | 8 | 1 | Finished in Sprint 1 | Inventory | Maintain a list of options for a desktop (e.g., disk, RAM, CPU) | Select them when designing a new desktop product
DESKT | 3 | 1 |  | 8 | 1 | Finished in Sprint 1 | Sales Staff | Define a new desktop configuration from options | Can quickly customize products for my customers
ORDER | 4 | 1 |  | 13 | 1 | Finished in Sprint 1 | Sales Staff | Associate a customer with one or more desktops into an order | Keep track of who has bought what
WIN | 5 | 2 |  | 21 | 2 | Finished in Sprint 2 | Sales Staff | Replace text interface with GUI main window | Use it more easily | Recommend baselining Nim from Lecture 13
OUTM | 6 | 2 |  | 5 | 2 | Finished in Sprint 2 | Sales Staff | Replace list of data records with main window list | Access the data directly in the window | Try using std::ostringstream to capture operator<< formatting
INDIA | 7 | 2 |  | 8 | 2 | Finished in Sprint 2 | Sales Staff | Replace data queries with series of dialogs | Do everything within the GUI | Recommend baselining EntryDialog from Lecture 14
ABOUT | 8 | 2 |  | 1 | 2 |  | Director | Provide About dialog for documenting licenses | Avoid a lawsuit
SAVE | 9 | 3 |  | 13 | 3 | Finished in Sprint 4 | Manager | Save the data to a default file (File > Save) | Persist our data through the years | This requires modifying the “model” to save and reload each object from a provided stream
SAVAS | 10 | 3 |  | 5 | 3 | Finished in Sprint 4 | Manager | Save the data to a specified file (File > Save As) | Persist our data through the years | Use Gtk::FileChooser
LOAD | 11 | 3 |  | 8 | 3 | Finished in Sprint 4 | Manager | Load the data from a specified file (File > Open) | Persist our data through the years | Use Gtk::FileChooser
QRAM | 12 | 4 |  | 21 | 3 | In Test | Customer | Store and display additional RAM data | Ensure I purchase the correct product | NOT WORKING :(
DCUST | 13 | 4 |  | 8 | 3 | Finished in Sprint 4 | Sales Staff | unified dialog for customer | Enter data more quickly
BONUS WORK – COMPLETE ABOVE FEATURES FIRST!!!
QCPU | 14 |  | 25 | 13 |  |  | Customer | Store and display additional CPU data | Ensure I purchase the correct product | Derive classes from Options and call operator<< polymorphically
QDISK | 15 |  | 10 | 5 |  |  | Customer | Store and display additional Disk data | Ensure I purchase the correct product
DORD | 16 |  | 15 | 8 |  | In Work | Sales Staff | Replace Insert Order dialogs with single dialog | Enter data more quickly
DOPT | 17 |  | 40 | 21 |  | In Work | Sales Staff | Replace Insert Option dialogs with single dialog | Enter data more quickly
DDESK | 18 |  | 25 | 13 |  | In Work | Sales Staff | Replace Insert Desktop dialogs with single dialog | Enter data more quickly
TBAR | 19 |  | 10 | 5 |  | Finished in Sprint 4 | Customer | Access key functionality with a toolbar AND menu | More quickly access the behaviors I need | You can baseline this code from Nim’s Mainwin::Mainwin as well
SCROL | 20 |  | 10 | 5 |  | In Work | Customer | Make the main window’s data area scrollable | See large volumes of data | The exact settings (e.g., are the scrollbars always visible or only when scrolling is available?) are up to you
DEPR | 21 |  | 25 | 13 |  |  | Inventory | Deprecate a product | Avoid selling products that are out of production | This requires a Boolean with getter and setter in the Options and Desktop classes to indicate which are deprecated. The index number may pose interesting challenges, since deprecation will create gaps.
SBAR | 22 |  | 15 | 8 |  |  | Manager | Replace the Gtk::Label for the status bar with Gtk::Statusbar, and maintain a message stack | Better track status of messages | Just swapping Gtk::Statusbar for Gtk::Label is trivial. Think through how to manage a first-in last-out stack of messages

## Sprint 04 Backlog
Sprint # | #REF! |  | Complete Fields in Green!!!
Start on | #REF! |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | #REF!
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 15
Day 1 Left | 15 | 0
Day 2 Left | 15 | 0
Day 3 Left | 15 | 0
Day 4 Left | 15 | 0
Day 5 Left | 13 | 2
Day 6 Left | 10 | 3
Day 7 Left | 7 | 3
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | WIN |  | exceptions for On_save_as, on_save, on_open function set up (Catch up from SP3) | Completed Day 5
2 | LOAD |  | Store: save customer and load customer using input/putput streams (Catch up from SP3) | Completed Day 5
3 | OUTM |  | Implement ostream and istream to Customer (Catch up from SP3) | Completed Day 6
4 | DESKT |  | Same for Store and Desktop (Catch up from SP3) | Completed Day 6
5 | ORDER |  | Same for Store and Order (Catch up from SP3) | Completed Day 6
6 | LOAD |  | Test error handling by writing out a file and analyze format (Catch up from SP3) | In Work
7 | QRAM |  | Store and display additional RAM data | In Work
8 | WIN |  | unified dialog for customer | Completed Day 7
9 | QRAM |  | Ability to enter RAM in insert_peripheral | Completed Day 7
10 | CUST |  | Store adjusted to load and store RAM objects (incomplete | In Work
11 | SCROL |  | Make the main window’s data area scrollable (BONUS) | In Work
12 | TBAR |  | Access key functionality with a toolbar AND menu (save, open, quit,new store) (BONUS) | Completed Day 7
13 | WIN |  | Replace Insert Desktop dialogs with single dialog (BONUS) | In Work
14 | WIN |  | Replace Insert Option dialogs with single dialog (BONUS) | In Work
15 | WIN |  | Replace Insert Order dialogs with single dialog (BONUS) | In Work
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 03 Backlog
Sprint # | #REF! |  | Complete Fields in Green!!!
Start on | #REF! |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | #REF!
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 9
Day 1 Left | 7 | 2
Day 2 Left | 6 | 1
Day 3 Left | 6 | 0
Day 4 Left | 6 | 0
Day 5 Left | 6 | 0
Day 6 Left | 6 | 0
Day 7 Left | 6 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | WIN |  | Install I/O Framework: matching pair member to class and 3 callaback methods and menu items | Completed Day 1
2 | SAVAS |  | Add Open and Save as Dialogs just as NIM code | Completed Day 1
3 | SAVE |  | On_save_as, on_save, on_open function set up | Completed Day 2
4 | WIN |  | Handle exceptions for above functions | In Work | do not have time
5 | LOAD |  | Store: save customer and load customer using input/putput streams | In Work | I am late in submission
6 | OUTM |  | Implement ostream and istream to Customer | In Work | do not have time
7 | DESKT |  | Same for Store and Desktop | In Work | do not have time
8 | ORDER |  | Same for Store and Order | In Work | do not have time
9 | WIN |  | Test error handling by writing out a file and analyze format | In Work | do not have time
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84